## Slide 1: Vulnerability A3.1 Clear Text Password (CTP) - Overview
Presence of cleartext credentials in application configuration and code files. These credentials can allow an intruder to easily move laterally into databases and other systems.

## Slide 2: Vulnerability A3.1 CTP – Remediation Plan
How we push changes to servers?
Take backup of existing Config files with .bk added in the name
Group policy Objects will be used to trigger ASP.NET IIS Registration Tool (Aspnet_regiis.exe) to encrypt or decrypt sections of a Web configuration file.
Default GPO refresh Interval : 90 minutes
Default Downtime : Zero minutes
How to detect if change happens?
Project team will run PowerShell commands on the server to verify if config file still returns with clear text information.
What happens if changes does not happen in 90 mins?
It’s a rare condition, Project team will apply encryption manually by logging into the server.
Rollback Plan
Unlink GPO if it is a mass number of servers or manually login and restore backup Config file.

## Slide 3: Vulnerability A3.1 Clear Text Password – Deployment Plan
***Time Zone shown in the table is Sydney, Melbourne Time (AEST)
DEPLOYMENT DATE |  | NON-CRITICAL |  |  |  |  |  | CRITICAL |  |  |  | 
 |  | Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H | Group I | Group I | Group J
 |  | 14-Sep | 19-Sep | 23-Sep | 24-Sep | 26-Sep | Patching window | 7-Oct | 8-Oct | 10-Oct | 15-Oct | Patching window
 |  | WED | MON | FRI | SAT | MON | Patching Day | FRI | SAT | MON | SAT | Patching Day
DEPLOYMENT | START | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | As per detailed mentioned in cmdb patching window & based on discussion with server Owner | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | As per detailed mentioned in cmdb patching window & based on discussion with server Owner
DEPLOYMENT | FINISH | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST |  | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 
DEPLOYMENT VALIDATION | START | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST |  | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 
DEPLOYMENT VALIDATION | FINISH | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST |  | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 
HYPERCARE - POST CHANGE | START | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST |  | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 
HYPERCARE - POST CHANGE | FINISH | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST |  | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 

## Slide 4: Vulnerability A3.1 Clear Text Password - Questions
Build remediation artefacts
Roll out Plan
Questions to Applications Owners:
What is your preferred deployment dates and time?
  Business days (business hours)
  Business days (outside business hours)
  Weekends
Will there be any application connected while remediation window? If Yes, will it affect remediation process.
Once encryption of credentials are done, are there any tests required to be executed?
Is there any Testing team member who can validate App workability after deployment?
Questions to Server Owners:
What is your preferred deployment dates and time/timezone?
  Business days (business hours)
  Business days (outside business hours)
  Weekends
Do you have any specific Sign Off criteria, which should be considered after deployment?
What is the hyper care period for this?