## Template _Deployment Plan - 6.2
Technical Lead:
Pilot Candidate:
Pilot Confirmed: | 52
Group Size - amount of servers per deployment | 8
Total Groups | 7
First Deployment | 2022-09-05 | 2022-09-07 | 2022-09-09
| Weekdays -Non business hours |  |  | Weekends |  | Weekdays - Non business hours
| Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H
Deployment Schedule | 2022-09-05 | 2022-09-07 | 2022-09-09 | 2022-09-10 | 2022-09-18 | 2022-09-12 | 2022-09-14 | 2022-09-16
Change deployment start | 18:00 | 18:00 | 18:00 | 9:00AM | 2:00PM | 6:00PM | 6:00PM | 6:00PM
Systems to be stopped prior the change ( suggest time to be executed by the server owner) | 5:30PM | 5:30PM | 5:30PM | 8:30AM | 1:30PM | 5:30PM | 5:30PM | 5:30PM
Change deployment completed | 6:30PM | 6:30PM | 6:30PM | 9:30AM | 2:30PM | 6:30PM | 6:30PM | 6:30PM
Post Change- Validation test start | 6:31PM | 6:31PM | 6:31PM | 9:31AM | 2:31PM | 6:31PM | 6:31PM | 6:31PM
Hypercare -Post Change-first Shift finish | 9:30PM | 9:30PM | 9:30PM | 10:00AM | 3:00PM | 9:30PM | 9:30PM | 9:30PM
Hypercare -Post Change -first Shift start | 8:00AM (following day) | 8:00AM (following day) | 8:00AM (following day) | n/a | 2:31PM | 8:00AM (following day) | 8:00AM (following day) | 8:00AM (following day)

## dep_control
Vulnerability | XXXX
Deployment Group | XXXX
Deployment Schedule | XXXX
Hostname | Project Team | Server Owner | Project Team | Project Team | ??? | ??? | Project Team | Project Team
| Send Comm(-1D) | Pre Deploy check | Deployment Start | Deployment Finish | Validation Start | Validation Finish | Hypercare start | Hypercare finish |  | Scheduled
Completed
Failed
Rescheduled
[9 empty] | NA | Not Required

## ProjSchedule
NTLM
|  | NON-CRITICAL |  |  |  |  | CRITICAL
|  | Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H | Group I
|  | 2022-09-12 | 2022-09-16 | 2022-09-17 | 2022-09-21 | 2022-09-23 | 2022-09-24 | 2022-09-26 | 2022-09-28 | 2022-10-08
|  | MON | FRI | SAT | WED | FRI | SAT | MON | WED | SAT
|  | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST
|  | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST
|  | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST
|  | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST
|  | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST
|  | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST
DEPLOYMENT DATE |  | 2022-09-12: NON-CRITICAL; 2022-09-24: CRITICAL
|  | Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H | Group I
|  | 2022-09-14 | 2022-09-19 | 2022-09-23 | 2022-09-24 | 2022-09-26 | 2022-10-07 | 2022-10-08 | 2022-10-10 | 2022-10-15
|  | WED | MON | FRI | SAT | MON | FRI | SAT | MON | SAT
DEPLOYMENT | START | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST
DEPLOYMENT | FINISH | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST
DEPLOYMENT VALIDATION | START | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST
DEPLOYMENT VALIDATION | FINISH | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST
HYPERCARE - POST CHANGE | START | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST
HYPERCARE - POST CHANGE | FINISH | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST
Deployment date |  | 2022-09-14: 2022-09-12; 2022-09-19: 2022-09-16; 2022-09-23: 2022-09-21; 2022-09-24: 2022-09-26
|  | MON | FRI | WED | MON
DEPLOYMENT | START | 2022-09-14: 8:00 AEST; 2022-09-19: 8:00 AEST; 2022-09-23: 8:00 AEST; 2022-09-24: 8:00 AEST
DEPLOYMENT | FINISH | 2022-09-14: 14:00 AEST; 2022-09-19: 14:00 AEST; 2022-09-23: 14:00 AEST; 2022-09-24: 14:00 AEST
DEPLOYMENT VALIDATION | START | 2022-09-14: 14:01 AEST; 2022-09-19: 14:01 AEST; 2022-09-23: 14:01 AEST; 2022-09-24: 14:01 AEST
DEPLOYMENT VALIDATION | FINISH | 2022-09-14: 15:00 AEST; 2022-09-19: 15:00 AEST; 2022-09-23: 15:00 AEST; 2022-09-24: 15:00 AEST
Hypercare -Post Change | START | 2022-09-14: 15:01 AEST; 2022-09-19: 15:01 AEST; 2022-09-23: 15:01 AEST; 2022-09-24: 15:01 AEST
Hypercare -Post Change | FINISH | 2022-09-14: 17:00 AEST; 2022-09-19: 17:00 AEST; 2022-09-23: 17:00 AEST; 2022-09-24: 17:00 AEST
Deployment date |  | 2022-09-14: 2022-09-14; 2022-09-19: 2022-09-19; 2022-09-23: 2022-09-23; 2022-09-24: 2022-09-28
|  | WED | MON | FRI | WED
DEPLOYMENT | START | 2022-09-14: 8:00 AEST; 2022-09-19: 8:00 AEST; 2022-09-23: 8:00 AEST; 2022-09-24: 8:00 AEST
DEPLOYMENT | FINISH | 2022-09-14: 13:00 AEST; 2022-09-19: 13:00 AEST; 2022-09-23: 13:00 AEST; 2022-09-24: 13:00 AEST
DEPLOYMENT VALIDATION | START | 2022-09-14: 13:01 AEST; 2022-09-19: 13:01 AEST; 2022-09-23: 13:01 AEST; 2022-09-24: 13:01 AEST
DEPLOYMENT VALIDATION | FINISH | 2022-09-14: 14:00 AEST; 2022-09-19: 14:00 AEST; 2022-09-23: 14:00 AEST; 2022-09-24: 14:00 AEST
Hypercare -Post Change | START | 2022-09-14: NDB 8:00 AEST; 2022-09-19: NDB 8:00 AEST; 2022-09-23: NDB 8:00 AEST; 2022-09-24: NDB 8:00 AEST
Hypercare -Post Change | FINISH | 2022-09-14: NDB 17:00 AEST; 2022-09-19: NDB 17:00 AEST; 2022-09-23: NDB 17:00 AEST; 2022-09-24: NDB 17:00 AEST

## NTLM
Workstream 3 - I4.3 ( NTLM v2)
Technical Lead: |  | Achroo |  |  | Deployment Date | 2022-09-07 | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-17 | 2022-09-19 | 2022-09-23 | 2022-10-08
Pilot Candidate: |  | 100 |  |  | Date of Change raised | 2022-08-29 | 2022-09-05 | 2022-09-07 | 2022-09-09 | 2022-09-09 | 2022-09-12 | 2022-09-16 | 2022-09-30
Pilot Confirmed: |  | 70 |  |  | Date of Change to be presented to CAB | 2022-08-30 | 2022-09-06 | 2022-09-08 | 2022-09-13 | 2022-09-13 | 2022-09-13 | 2022-09-20 | 2022-10-04
Critical |  | 20 |  |  | Week | Week 6 | Week 7 | Week 7 | Week 8 | Week 8 | Week 8 | Week 9 | Week 11
Non Critical |  | 50 |  |  | Sprint | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 4
Group Size ( Max) - amount of servers per deployment
Group Size Critical |  | 10+10
Group Size Non Critical |  | 15+15+20
Total Groups
Nos.of Group Non Critical ( Weekdays+Weekends) |  | 4+1
Nos.of Group Critical ( Weekdays+Weekends) |  | 2+2
Deployment - Non Critical Weekdays |  |  | 2022-09-12 | 2022-09-16 | 2022-09-21 | 2022-08-30: 2022-09-23
Deployment - Non Critical Weekends |  |  |  | 2022-09-17 | bar: 2022-08-30
Deployment -Critical Weekdays |  |  | 2022-09-26 | 2022-09-28 | bar: 2022-08-30
Deployment - Critical Weekends |  | 2022-09-24 |  |  | 2022-10-08 | bar: 2022-08-30
NTLM | bar: 2022-08-30 to 2022-09-13
DEPLOYMENT DATE |  | NON-CRITICAL |  |  |  | 2022-09-06: CRITICAL
|  | Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H | Group I
|  | 2022-09-12 | 2022-09-16 | 2022-09-17 | 2022-09-21 | 2022-09-23 | 2022-09-24 | 2022-09-26 | 2022-09-28 | 2022-10-08
|  | MON | FRI | SAT | WED | FRI | SAT | MON | WED | SAT
DEPLOYMENT | START | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST
DEPLOYMENT | FINISH | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST
DEPLOYMENT VALIDATION | START | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST
DEPLOYMENT VALIDATION | FINISH | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST
HYPERCARE - POST CHANGE | START | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST
HYPERCARE - POST CHANGE | FINISH | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST
150

## CTP
Workstream1 - A3.1 (CTP)
Technical Lead: | Achroo |  | Deployment Date | 2022-09-07 | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-17 | 2022-09-19 | 2022-09-23 | 2022-09-24
Pilot Candidate: | 100 |  | Date of Change raised | 2022-08-29 | 2022-09-05 | 2022-09-07 | 2022-09-09 | 2022-09-09 | 2022-09-12 | 2022-09-16 | 2022-09-16
Pilot Confirmed: | 70 |  | Date of Change to be presented to CAB | 2022-08-30 | 2022-09-06 | 2022-09-08 | 2022-09-13 | 2022-09-13 | 2022-09-13 | 2022-09-20 | 2022-09-20
Critical | 20 |  | Week | Week 6 | Week 7 | Week 7 | Week 8 | Week 8 | Week 8 | Week 9 | Week 9
Non Critical | 50 |  | Sprint | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3
Group Size ( Max) - amount of servers per deployment
Group Size Critical | 10+10
Group Size Non Critical | 15+15+20
Total Groups
Nos.of Group Non Critical ( Weekdays+Weekends) | 4+1
Nos.of Group Critical ( Weekdays+Weekends) | 2+2
Deployment - Non Critical Weekdays |  | 2022-09-14 | 2022-09-19 | 2022-08-30: 2022-09-23; 2022-09-06: 2022-09-26
Deployment - Non Critical Weekends |  |  |  | 2022-08-30: 2022-09-24
Deployment -Critical Weekdays |  | 2022-10-07 | 2022-10-10 | bar: 2022-08-30 to 2022-09-06
Deployment - Critical Weekends |  | 2022-10-08 |  | 2022-08-30: 2022-10-15
DEPLOYMENT DATE |  | NON-CRITICAL |  | 2022-09-13: CRITICAL
|  | Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H | Group I
|  | 2022-09-14 | 2022-09-19 | 2022-09-23 | 2022-09-24 | 2022-09-26 | 2022-10-07 | 2022-10-08 | 2022-10-10 | 2022-10-15
|  | WED | MON | FRI | SAT | MON | FRI | SAT | MON | SAT
DEPLOYMENT | START | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST | 8:00 AEST
DEPLOYMENT | FINISH | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST | 11:00 AEST
DEPLOYMENT VALIDATION | START | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST | 12:00 AEST
DEPLOYMENT VALIDATION | FINISH | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST | 15:00 AEST
HYPERCARE - POST CHANGE | START | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST | 15:01 AEST
HYPERCARE - POST CHANGE | FINISH | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST | 18:00 AEST

## PowerShell
|  |  |  | Deployment Date | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-21 | 2022-09-23
Workstream 4 - I4.5 (Powershell 2.0) |  |  |  | Date of Change raised | 2022-09-05 | 2022-09-07 | 2022-09-09 | 2022-09-09 | 2022-09-09 | 2022-09-12 | 2022-09-14 | 2022-09-16
Technical Lead: |  | Alex |  | Date of Change to be presented to CAB | 2022-09-06 | 2022-09-08 | 2022-09-13 | 2022-09-13 | 2022-09-13 | 2022-09-13 | 2022-09-15 | 2022-09-20
Pilot Candidate: |  | 60 |  | Week | Week 7 | Week 7 | Week 8 | Week 8 | Week 8 | Week 8 | Week 8 | Week 9
Pilot Confirmed: |  | 50 |  | Sprint | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3
Group Size ( Max) - amount of servers per deployment |  | 15
Total Groups ( Weekdays and Weekends) |  | 5+2
Deployment - Weekdays |  | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-06: 2022-09-19; 2022-09-08: 2022-09-21; 2022-09-13: 2022-09-23
Deployment - Weekends |  |  |  | 2022-09-17 | 2022-09-06: 2022-09-18
Deployment date |  | 2022-09-12 | 2022-09-16 | 2022-09-21 | 2022-09-06: 2022-09-26
|  | MON | FRI | WED | 2022-09-06: MON
DEPLOYMENT | START | 8:00 AEST | 8:00 AEST | 8:00 AEST | 2022-09-06: 8:00 AEST
DEPLOYMENT | FINISH | 14:00 AEST | 14:00 AEST | 14:00 AEST | 2022-09-06: 14:00 AEST
DEPLOYMENT VALIDATION | START | 14:01 AEST | 14:01 AEST | 14:01 AEST | 2022-09-06: 14:01 AEST
DEPLOYMENT VALIDATION | FINISH | 15:00 AEST | 15:00 AEST | 15:00 AEST | 2022-09-06: 15:00 AEST
Hypercare -Post Change | START | 15:01 AEST | 15:01 AEST | 15:01 AEST | 2022-09-06: 15:01 AEST
Hypercare -Post Change | FINISH | 17:00 AEST | 17:00 AEST | 17:00 AEST | 2022-09-06: 17:00 AEST

## RDP
|  |  | Deployment Date | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-21 | 2022-09-23
|  |  | Date of Change raised | 2022-09-05 | 2022-09-07 | 2022-09-09 | 2022-09-09 | 2022-09-09 | 2022-09-12 | 2022-09-14 | 2022-09-16
Workstream 2 - I 4.1 (RDP) |  |  | Date of Change to be presented to CAB | 2022-09-06 | 2022-09-08 | 2022-09-13 | 2022-09-13 | 2022-09-13 | 2022-09-13 | 2022-09-15 | 2022-09-20
Technical Lead: | Alex |  | Week | Week 7 | Week 7 | Week 8 | Week 8 | Week 8 | Week 8 | Week 8 | Week 9
Pilot Candidate: | 60 |  | Sprint | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3
Pilot Confirmed: | 50
Group Size ( Max) - amount of servers per deployment | 15
Total Groups ( Weekdays and Weekends) | 5+2
Deployment - Weekdays | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-06: 2022-09-19; 2022-09-08: 2022-09-21; 2022-09-13: 2022-09-23
Deployment - Weekends |  |  | 2022-09-17 | 2022-09-06: 2022-09-18
Deployment date |  | 2022-09-14 | 2022-09-19 | 2022-09-06: 2022-09-23; 2022-09-08: 2022-09-28
|  | WED | MON | 2022-09-06: FRI; 2022-09-08: WED
DEPLOYMENT | START | 8:00 AEST | 8:00 AEST | 2022-09-06: 8:00 AEST; 2022-09-08: 8:00 AEST
DEPLOYMENT | FINISH | 13:00 AEST | 13:00 AEST | 2022-09-06: 13:00 AEST; 2022-09-08: 13:00 AEST
DEPLOYMENT VALIDATION | START | 13:01 AEST | 13:01 AEST | 2022-09-06: 13:01 AEST; 2022-09-08: 13:01 AEST
DEPLOYMENT VALIDATION | FINISH | 14:00 AEST | 14:00 AEST | 2022-09-06: 14:00 AEST; 2022-09-08: 14:00 AEST
Hypercare -Post Change | START | NDB 8:00 AEST | NDB 8:00 AEST | 2022-09-06: NDB 8:00 AEST; 2022-09-08: NDB 8:00 AEST
Hypercare -Post Change | FINISH | NDB 17:00 AEST | NDB 17:00 AEST | 2022-09-06: NDB 17:00 AEST; 2022-09-08: NDB 17:00 AEST