## Template _Deployment Plan - 6.2
Technical Lead:
Pilot Candidate:
Pilot Confirmed: | 52
Group Size - amount of servers per deployment | 8
Total Groups | 7
First Deployment | 2022-09-05 | 2022-09-07 | 2022-09-09
| Weekdays -Non business hours |  |  | Weekends |  | Weekdays - Non business hours
| Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H
Deployment Schedule | 2022-09-05 | 2022-09-07 | 2022-09-09 | 2022-09-10 | 2022-09-18 | 2022-09-12 | 2022-09-14 | 2022-09-16
Change deployment start | 18:00 | 18:00 | 18:00 | 9:00AM | 2:00PM | 6:00PM | 6:00PM | 6:00PM
Systems to be stopped prior the change ( suggest time to be executed by the server owner) | 5:30PM | 5:30PM | 5:30PM | 8:30AM | 1:30PM | 5:30PM | 5:30PM | 5:30PM
Change deployment completed | 6:30PM | 6:30PM | 6:30PM | 9:30AM | 2:30PM | 6:30PM | 6:30PM | 6:30PM
Post Change- Validation test start | 6:31PM | 6:31PM | 6:31PM | 9:31AM | 2:31PM | 6:31PM | 6:31PM | 6:31PM
Hypercare -Post Change-first Shift finish | 9:30PM | 9:30PM | 9:30PM | 10:00AM | 3:00PM | 9:30PM | 9:30PM | 9:30PM
Hypercare -Post Change -first Shift start | 8:00AM (following day) | 8:00AM (following day) | 8:00AM (following day) | n/a | 2:31PM | 8:00AM (following day) | 8:00AM (following day) | 8:00AM (following day)

## CTP
Workstream1 - A3.1 (CTP)
Technical Lead: | Achroo
Pilot Candidate: | 100
Pilot Confirmed: | 70
Critical | 20
Non Critical | 50
Group Size ( Max) - amount of servers per deployment
Group Size Critical | 10
Group Size Non Critical | 15
Total Groups
Nos.of Group Non Critical ( Weekdays+Weekends) | 4+2
Nos.of Group Critical ( Weekdays+Weekends) | 3+2
Deployment - Non Critical Weekdays |  | 2022-09-07 | 2022-09-12 | 2022-09-14 | 2022-09-16
Deployment - Non Critical Weekends |  |  |  | 2022-09-17
Deployment -Critical Weekdays | 2022-09-19 |  | 2022-09-23
Deployment - Critical Weekends |  |  | 2022-09-24
Details | Non-critical |  |  |  |  | Critical
| Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H
| 2022-09-07 | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-17 | 2022-09-19 | 2022-09-23 | 2022-09-24
Change deployment start | 9:00AM | 9:00AM | 3:00PM | 3:00PM | 11:00AM | 9:00AM | 3:00PM | 11:00AM
Systems to be stopped prior the change ( suggest time to be executed by the server owner) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Change deployment completed | 10:00AM | 10:00AM | 4:00PM | 4:00PM | 12:00PM | 10:00AM | 4:00PM | 12:00PM
Post Change- Validation test start | 10:01AM | 10:01AM | 4:01PM | 4:01PM | 12:01PM | 10:01AM | 4:01PM | 12:01PM
Hypercare -Post Change-first shift start | 11:00AM | 11:00AM | 5:00PM | 5:00PM | 1:00PM | 11:00AM | 5:00PM | 1:00PM
Hypercare -Post Change -first Shift finish | 1:00PM | 1:00PM | 7:00PM | 7:00PM | 3:00PM | 1:00PM | 7:00PM | 3:00PM

## RDP
Workstream 2 - I 4.1 (RDP)
Technical Lead: | Alex
Pilot Candidate: | 60
Pilot Confirmed: | 50
Group Size ( Max) - amount of servers per deployment | 15
Total Groups ( Weekdays and Weekends) | 5+2
Deployment - Weekdays | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-19 | 2022-09-21
Deployment - Weekends |  |  | 2022-09-17 | 2022-09-18
| Weekdays -Non business hours |  |  | Weekends |  | Weekdays - Non business hours
| Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H
Change deployment start | 18:00 | 18:00 | 18:00 | 9:00AM | 2:00PM | 6:00PM | 6:00PM | 6:00PM
Systems to be stopped prior the change ( suggest time to be executed by the server owner) | 5:30PM | 5:30PM | 5:30PM | 8:30AM | 1:30PM | 5:30PM | 5:30PM | 5:30PM
Change deployment completed | 6:30PM | 6:30PM | 6:30PM | 9:30AM | 2:30PM | 6:30PM | 6:30PM | 6:30PM
Post Change- Validation test start | 6:31PM | 6:31PM | 6:31PM | 9:31AM | 2:31PM | 6:31PM | 6:31PM | 6:31PM
Hypercare -Post Change-first Shift finish | 9:30PM | 9:30PM | 9:30PM | 10:00AM | 3:00PM | 9:30PM | 9:30PM | 9:30PM
Hypercare -Post Change -first Shift start | 8:00AM (following day) | 8:00AM (following day) | 8:00AM (following day) | n/a | 2:31PM | 8:00AM (following day) | 8:00AM (following day) | 8:00AM (following day)

## NTLM
Workstream 3 - I4.3 ( NTLM v2)
Technical Lead: | Achroo
Pilot Candidate: | 100
Pilot Confirmed: | 70
Critical | 20
Non Critical | 50
Group Size ( Max) - amount of servers per deployment
Group Size Critical | 10
Group Size Non Critical | 15
Total Groups
Nos.of Group Non Critical ( Weekdays+Weekends) | 4+2
Nos.of Group Critical ( Weekdays+Weekends) | 3+2
Deployment - Non Critical Weekdays |  | 2022-09-07 | 2022-09-12 | 2022-09-14 | 2022-09-16
Deployment - Non Critical Weekends |  |  |  | 2022-09-17
Deployment -Critical Weekdays | 2022-09-19 |  | 2022-09-23
Deployment - Critical Weekends |  |  | 2022-10-08
Details | Non-critical |  |  |  |  | Critical
| Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H
| 2022-09-07 | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-18 | 2022-09-19 | 2022-09-23 | 2022-10-08
Change deployment start | 3:00PM | 3:00PM | 9:00AM | 9:00AM | 11:00AM | 3:00PM | 9:00AM | 11:00AM
Systems to be stopped prior the change ( suggest time to be executed by the server owner) | As Applicable | As Applicable | As Applicable | As Applicable | As Applicable | As Applicable | As Applicable | As Applicable
Change deployment completed | 4:00PM | 4:00PM | 10:00AM | 10:00AM | 12:00PM | 4:00PM | 10:00AM | 12:00PM
Post Change- Validation test start | 4:01PM | 4:01PM | 10:01AM | 10:01AM | 12:01PM | 4:01PM | 10:01AM | 12:01PM
Hypercare -Post Change-first shift start | 5:00PM | 5:00PM | 11:00AM | 11:00AM | 1:00PM | 5:00PM | 11:00AM | 1:00PM
Hypercare -Post Change -first Shift finish | 7:00PM | 7:00PM | 1:00PM | 1:00PM | 3:00PM | 7:00PM | 1:00PM | 3:00PM

## PowerShell
Workstream 4 - I4.5 (Powershell v2)
Technical Lead: | Alex
Pilot Candidate: | 60
Pilot Confirmed: | 50
Group Size ( Max) - amount of servers per deployment | 15
Total Groups ( Weekdays and Weekends) | 5+2
Deployment - Weekdays | 2022-09-12 | 2022-09-14 | 2022-09-16 | 2022-09-19 | 2022-09-21
Deployment - Weekends |  |  | 2022-09-17 | 2022-09-18
| Weekdays -Non business hours |  |  | Weekends |  | Weekdays - Non business hours
| Group A | Group B | Group C | Group D | Group E | Group F | Group G | Group H
Change deployment start | 18:00 | 18:00 | 18:00 | 9:00AM | 2:00PM | 6:00PM | 6:00PM | 6:00PM
Systems to be stopped prior the change ( suggest time to be executed by the server owner) | 5:30PM | 5:30PM | 5:30PM | 8:30AM | 1:30PM | 5:30PM | 5:30PM | 5:30PM
Change deployment completed | 6:30PM | 6:30PM | 6:30PM | 9:30AM | 2:30PM | 6:30PM | 6:30PM | 6:30PM
Post Change- Validation test start | 6:31PM | 6:31PM | 6:31PM | 9:31AM | 2:31PM | 6:31PM | 6:31PM | 6:31PM
Hypercare -Post Change-first Shift finish | 9:30PM | 9:30PM | 9:30PM | 10:00AM | 3:00PM | 9:30PM | 9:30PM | 9:30PM
Hypercare -Post Change -first Shift start | 8:00AM (following day) | 8:00AM (following day) | 8:00AM (following day) | n/a | 2:31PM | 8:00AM (following day) | 8:00AM (following day) | 8:00AM (following day)

## Date
NTLM / CTP |  |  |  | NC - 5 batches |  | NC - 2 batches
2022-09-12 | 2022-09-16 | Week 8 | NC - 5 batches | 12,14,16 | WD | 17,18 | WKS
2022-09-19 | 2022-09-23 | Week 9 | NC - 2 batches | 19,21,23 | WD | 24 | WKS
2022-09-26 | 30 | week 10 | C - 3 batches | 26,28 | WD | 0 | WKS
2022-10-03 | 2022-10-07 | week 11 | C- 2 batches | 7 | WD | 8,9 | WKS