## Build Tasks
Name | Provider | Start_Date | Finish_Date | Duration | Man Hours
LL Design |  | 2022-08-15 08:00 | 2022-11-10 17:00 | 63 days?
Low level design for automation |  | 2022-08-15 08:00 | 2022-11-10 17:00 | 63 days?
Draft Low level design for automation | Rajesh | 2022-08-15 08:00 | 2022-08-26 17:00 | 2 wks
Review Low level design for automation | Rajesh | 2022-08-29 08:00 | 2022-09-09 17:00 | 2 wks
Hand Over to Avanade | Rajesh | 2022-10-05 08:00 | 2022-10-05 17:00 | 1 day
Review and complete LL infradesign | Avanade | 2022-10-10 08:00 | 2022-10-27 17:00 | 14 days
Send LLD Architecture Document for ARB review and approval | Avanade | 2022-10-28 08:00 | 2022-11-10 17:00 | 10 days?
Design 1: LL Design Architecture Document - Completed and Signed-off | Avande | 2022-10-28 08:00 | 2022-10-28 08:00 | 0 days
Migration Framework Build | Owner | Start | Finish | Duration | Man Hours | Category | Assignee | Status | ETC | Notes:
Provision Azure Express Route | CFS |  |  |  | 0 | Express Route
Provision Azure Express Route Gateway | CFS |  |  |  | 0 | Express Route
V-Net Peering - CFS Landing Zone to CFS Migration Data Platform | CFS |  |  |  | 0 | Vnet Peering
Provision Azure Data Factory | Ava | 2022-10-14 08:00 | 2022-12-01 17:00 | 35 days | 0 | Bicep Template | Infra (Jojo) |  | 0
Create and unit-test Non-prod Bicep template | Ava | 2022-10-14 08:00 | 2022-10-17 17:00 | 2 days | 18 | Bicep Template | Infra (Jojo) | Complete | 0
Test deployment of ADF using Bicep in non-prod | Ava | 2022-10-28 08:00 | 2022-11-10 17:00 | 10 days |  | Bicep Template |  |  | 0
Submit template to CFS - John S. for review | CFS | 2022-10-28 08:00 | 2022-11-02 17:00 | 4 days | 0 | Bicep Template | Infra (Jojo) |  | 0
Update template based on feedback and send for sign-off | Ava | 2022-11-03 08:00 | 2022-11-16 17:00 | 10 days | 90 | Bicep Template | Infra (Jojo) | Complete | 0
Approve/Sign-off Bicep template | CFS | 2022-11-17 | 2022-11-17 | 1 day | 0 | Bicep Template |  |  | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 1 day | 4 | Bicep Template | Infra (Jojo) | Not Started | 4
Deploy to Pre-prod environment using Bicep template | Ava | 2022-11-28 | 2022-11-28 | 1 day | 9 | Bicep Template | Infra (Jojo) | Complete | 0
Test deployment to pre-prod using Bicep template | Ava | 2022-11-29 | 2022-11-29 | 1 day | 9 | Bicep Template | Infra (Jojo) | Complete | 0
Deploy to Prod environment using Bicep template | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | Bicep Template - Deploy | Infra (Jojo) | Not Started | 9
Test deployment in Prod using Bicep template | Ava | 2022-12-19 | 2022-12-19 | 1 day | 9 | Bicep Template - Deploy | Infra (Jojo) | Not Started | 9
Provision Azure Data Factory self-hosted runtime |  | 2022-10-17 08:00 | 2022-12-01 17:00 |  | 0 | Bicep Template
Provision VM (to install the runtime) | Ava | 2022-10-17 08:00 | 2022-10-18 17:00 | 2 days | 18 | Bicep Template | Achroo | Complete | 0
Domain join the VM | Ava | 2022-10-18 08:00 | 2022-10-18 17:00 | 1 day | 9 | Bicep Template | Achroo | Complete | 0
Download SHIR and install SHIR | Ava | 2022-10-18 08:00 | 2022-10-18 17:00 | 1 day | 9 | Bicep Template | Achroo | Complete | 0
Establish hand-share with ADF | Ava | 2022-10-19 08:00 | 2022-10-19 17:00 | 1 day | 9 | Bicep Template | Achroo | Complete | 0
Test ADF - SHIR connectivity | Ava | 2022-10-20 08:00 | 2022-10-20 17:00 | 1 day | 9 | Bicep Template | Achroo | Complete | 0
Create image template and install in image gallery | Ava | 2022-10-21 08:00 | 2022-10-21 17:00 | 1 day | 9 | Bicep Template | Achroo | Complete | 0
Create Bicep template to provision image gallery | Ava | 2022-10-21 08:00 | 2022-10-21 17:00 | 1 day | 9 | Bicep Template | Achroo | Complete | 0
Test deployment using Bicep in non-prod | Ava | 2022-10-28 08:00 | 2022-11-10 17:00 | 10 days | 0 | Bicep Template
Submit template to CFS (John S.) for review | CFS | 2022-10-28 08:00 | 2022-11-02 17:00 | 4 days | 0 | Bicep Template | Infra (Jojo) |  | 0
Update template based on feedback and send for sign-off | Ava | 2022-11-03 08:00 | 2022-11-15 17:00 | 10 days | 90 | Bicep Template | Infra (Jojo) | Complete | 0
Approve/signoff Bicep template | CFS | 2022-11-07 08:00 | 2022-11-07 17:00 | 1 day | 0 | Bicep Template | Infra (Jojo) |  | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 1 day | 4 | Bicep Template | Infra (Jojo) | Not Started | 4
Deploy to Pre-prod environment using Bicep template | Ava | 2022-11-28 | 2022-11-28 | 1 day | 9 | Bicep Template | Infra (Jojo) | Complete | 0
Test deployment in Pre-prod using Bicep template | Ava | 2022-11-29 | 2022-11-29 | 1 day | 9 | Bicep Template | Infra (Jojo) | Complete | 0
Deploy to Prod environment using Bicep template | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | Bicep Template - Deploy | Infra (Jojo) |  | 9
Test deployment in Prod using Bicep template | Ava | 2022-12-19 | 2022-12-19 | 1 day | 9 | Bicep Template - Deploy | Infra (Jojo) |  | 9
Provision Azure SQL Database using Bicep template | Ava | 2022-10-14 08:00 | 2022-12-01 17:00 | 35 days | 0 | Bicep Template |  |  | 0
Create and unit-test Non-prod Bicep template | Ava | 2022-10-14 08:00 | 2022-10-17 17:00 | 2 days | 18 | Bicep Template | Rhoda | Complete | 0
Test deployment of SQL DB using Bicep in non-prod | Ava | 2022-10-28 08:00 | 2022-11-10 17:00 | 10 days | 0 | Bicep Template | Rhoda |  | 0
Submit template to CFS - John S. for review | CFS | 2022-10-28 08:00 | 2022-11-02 17:00 | 4 days | 0 | Bicep Template | Rhoda |  | 0
Update template based on feedback and send for sign-off | Ava | 2022-11-03 08:00 | 2022-11-15 17:00 | 10 days | 90 | Bicep Template | Rhoda | Complete | 0
Approve/Sign-off Bicep template | CFS | 2022-11-07 08:00 | 2022-11-07 17:00 | 1 day | 0 | Bicep Template | Rhoda |  | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 1 day | 4 | Bicep Template | Rhoda | Not Started | 4
Deploy to Pre-prod environment using Bicep template | Ava | 2022-11-28 | 2022-11-28 | 1 day | 9 | Bicep Template | Rhoda | Complete | 0
Test deployment to pre-prod using Bicep template | Ava | 2022-11-29 | 2022-11-29 | 1 day | 9 | Bicep Template | Rhoda | Not Started | 9
Deploy to Prod environment using Bicep template | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | Bicep Template - Deploy | Rhoda |  | 9
Test deployment in Prod using Bicep template |  | 2022-12-19 | 2022-12-19 |  |  | Bicep Template - Deploy
Define Service Plan |  | 2022-10-17 08:00 | 2022-10-18 17:00 | 2 days | 0 | Bicep Template |  |  | 0
Finalize service plan allocation for prod non prod | Ava | 2022-10-17 08:00 | 2022-10-18 17:00 | 2 days | 18 | Bicep Template | Infra (Jojo) | Complete | 0
Provision Azure VM using Bicep template | Ava | 2022-10-18 08:00 | 2022-12-01 17:00 | 33 days |  | Bicep Template |  |  | 0
Leverage and modify existing template with CFS (or create a new one) | Ava | 2022-10-18 08:00 | 2022-10-19 17:00 | 2 days | 18 | Bicep Template | Infra (Jojo) | Complete | 0
Test deployment of Azure VM in Non-prod using Bicep template |  | 2022-10-28 08:00 | 2022-11-10 17:00 | 10 days |  | Bicep Template |  |  | 0
Submit template to CFS (John S.) for review | CFS | 2022-10-28 08:00 | 2022-11-02 17:00 | 4 days | 0 | Bicep Template | Infra (Jojo) |  | 0
Update template based on feedback and send for sign-off | Ava | 2022-11-03 08:00 | 2022-11-15 17:00 | 10 days | 90 | Bicep Template | Infra (Jojo) | Complete | 0
Approve/signoff Bicep template | CFS | 2022-11-07 08:00 | 2022-11-07 17:00 | 1 day | 0 | Bicep Template | Infra (Jojo) |  | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 1 day | 4 | Bicep Template | Infra (Jojo) | Not Started | 4
Deploy to Pre-prod environment using Bicep template | Ava | 2022-11-28 | 2022-11-28 | 1 day | 9 | Bicep Template | Infra (Jojo) | Not Started | 9
Test deployment in Pre-prod using Bicep template | Ava | 2022-11-29 | 2022-11-29 | 1 day | 9 | Bicep Template | Infra (Jojo) | Not Started | 9
Deploy in Prod environment using Bicep template | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | Bicep Template - Deploy | Infra (Jojo) | Not Started | 9
Test deployment in Prod using Bicep template | Ava | 2022-12-19 | 2022-12-19 | 1 day | 9 | Bicep Template - Deploy | Infra (Jojo) | Not Started | 9
Provision Azure Blob Storage using Bicep template | Ava | 2022-10-14 08:00 | 2022-12-01 17:00 | 35 days |  | Bicep Template |  |  | 0
Leverage and modify existing template (or create a new one) | Ava | 2022-10-14 08:00 | 2022-10-17 17:00 | 2 days | 18 | Bicep Template | Infra (Jojo) | Complete | 0
Test deployment of Azure VM in Non-prod using Bicep template |  | 2022-10-28 08:00 | 2022-11-10 17:00 | 10 days |  | Bicep Template |  |  | 0
Submit template to CFS (John S.) for review | CFS | 2022-10-28 08:00 | 2022-11-02 17:00 | 4 days | 0 | Bicep Template | Infra (Jojo) |  | 0
Update template based on feedback and send for sign-off | Ava | 2022-11-03 08:00 | 2022-11-15 17:00 | 10 days | 90 | Bicep Template | Infra (Jojo) | Complete | 0
Approve/signoff Bicep template | CFS | 2022-11-09 08:00 | 2022-11-09 17:00 | 1 day | 0 | Bicep Template | Infra (Jojo) |  | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 1 day | 4 | Bicep Template | Infra (Jojo) | Not Started | 4
Deploy to Pre-prod environment using Bicep template | Ava | 2022-11-28 | 2022-11-28 | 1 day | 9 | Bicep Template | Infra (Jojo) | Not Started | 0
Test deployment in pre-prod using Bicep template | Ava | 2022-11-29 | 2022-11-29 | 1 day | 9 | Bicep Template | Infra (Jojo) | Not Started | 9
Deploy in Prod environment using Bicep template | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | Bicep Template - Deploy | Infra (Jojo) | Not Started | 9
Test deployment in Prod using Bicep template | Ava | 2022-12-19 | 2022-12-19 | 1 day | 9 | Bicep Template - Deploy | Infra (Jojo) | Not Started | 9
Provision Service Endpoint | Ava | 2022-10-17 08:00 | 2022-12-01 17:00 | 34 days? |  | Bicep Template |  |  | 0
Leverage and modify existing template (or create a new one) | Ava | 2022-10-17 08:00 | 2022-10-18 17:00 | 2 days | 18 | Bicep Template | Achroo | Complete | 0
Test deployment of End Point in Non-prod using Bicep template |  | 2022-10-28 08:00 | 2022-11-10 17:00 | 10 days |  | Bicep Template |  |  | 0
Submit template to CFS (John S.) for review | CFS | 2022-10-28 08:00 | 2022-11-02 17:00 | 4 days | 0 | Bicep Template | Infra (Jojo) |  | 0
Update template based on feedback and send for sign-off | Ava | 2022-11-03 08:00 | 2022-11-15 17:00 | 10 days | 90 | Bicep Template | Achroo | Complete | 0
Approve/signoff Bicep template | CFS | 2022-11-07 08:00 | 2022-11-07 17:00 | 1 day | 0 | Bicep Template | Infra (Jojo) |  | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 1 day | 4 | Bicep Template | Achroo | Not Started | 4
Deploy to Pre-prod environment using Bicep template | Ava | 2022-11-28 | 2022-11-28 | 1 day | 9 | Bicep Template | Achroo | Not Started | 9
Test deployment in pre-prod using Bicep template | Ava | 2022-11-29 | 2022-11-29 | 1 day | 9 | Bicep Template | Achroo | Not Started | 9
Deploy in Prod environment using Bicep template | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | Bicep Template - Deploy | Achroo | Not Started | 9
Test deployment in Prod environment using Bicep template | Ava | 2022-12-19 | 2022-12-19 | 1 day? | 9 | Bicep Template - Deploy | Achroo | Not Started | 9
Azure Databox | CFS | 2022-10-10 08:00 | 2022-10-10 17:00 | 1 day |  | Azure Databox |  |  | 0
V-Net Peering - CFS Migration Data Platform to CFS Main Hub | Ava | 2022-11-21 | 2022-11-25 | 5 days? | 45 | Bicep Template | Rhoda | Not Started | 9
Provision Azure Keyvault |  | 2022-10-20 08:00 | 2022-12-01 17:00 | 31 days |  |  |  |  | 0
Create and unit-test Non-prod Bicep template | Ava | 2022-10-20 08:00 | 2022-10-24 17:00 | 3 days | 27 | Bicep Template | Rhoda | Complete | 0
Test deployment of Azure Keyvault using Bicep in non-prod | Ava | 2022-10-28 08:00 | 2022-11-10 17:00 | 10 days |  |  | Rhoda |  | 0
Submit template to CFS - John S. for review | Ava | 2022-10-28 08:00 | 2022-11-02 17:00 | 4 days | 0 | Bicep Template | Rhoda |  | 0
Update template based on feedback and send for sign-off | Ava | 2022-11-03 08:00 | 2022-11-15 17:00 | 10 days | 90 | Bicep Template | Rhoda | Complete | 0
Approve/Sign-off Bicep template | Ava | 2022-11-07 08:00 | 2022-11-07 17:00 | 1 day | 0 | Bicep Template | Rhoda |  | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 1 day | 4 | Bicep Template | Rhoda | Not Started | 4
Deploy to Pre-prod environment using Bicep template | Ava | 2022-11-28 | 2022-11-28 | 1 day | 9 | Bicep Template | Rhoda | Not Started | 9
Test deployment to pre-prod using Bicep template | Ava | 2022-11-29 | 2022-11-29 | 1 day | 9 | Bicep Template | Rhoda | Not Started | 9
Deploy to Prod environment using Bicep template | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | Bicep Template - Deploy | Rhoda |  | 9
Test deployment in Prod using Bicep template |  | 2022-12-19 | 2022-12-19 |  |  | Bicep Template - Deploy
Provision Azure Functions |  | 2022-10-25 08:00 | 2022-12-01 17:00 | 28 days |  | Bicep Template |  |  | 0
Agree on Non-prod Azure Function Plan | CFS, Ava | 2022-10-25 08:00 | 2022-10-25 17:00 | 1 day | 9 | Bicep Template | Achroo | Complete | 0
Create Bicep template for Azure Function | Ava | 2022-10-26 08:00 | 2022-11-01 17:00 | 5 days | 45 | Bicep Template | Achroo | Complete | 0
Test deployment of Azure Function in Non-prod using Bicep template |  | 2022-11-02 08:00 | 2022-11-15 17:00 | 10 days |  | Bicep Template |  |  | 0
Submit template to CFS (John S.) for review | CFS | 2022-11-02 08:00 | 2022-11-07 17:00 | 4 days | 0 | Bicep Template | Infra (Jojo) |  | 0
Update template based on feedback and send for sign-off | Ava | 2022-11-03 08:00 | 2022-11-15 17:00 | 10 days | 90 | Bicep Template | Infra (Jojo) | Complete | 0
Approve/signoff Bicep template | CFS | 2022-11-10 08:00 | 2022-11-10 17:00 | 1 day | 0 | Bicep Template | Infra (Jojo) |  | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 1 day | 4 | Bicep Template | Achroo | Not Started | 4
Deploy to Pre-prod environment using Bicep template | Ava | 2022-11-28 | 2022-11-28 | 1 day | 9 | Bicep Template | Achroo | Not Started | 9
Test deployment in pre-prod using Bicep template | Ava | 2022-11-29 | 2022-11-29 | 1 day | 9 | Bicep Template | Achroo | Not Started | 9
Deploy in Prod environment using Bicep template | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | Bicep Template - Deploy | Achroo | Not Started | 9
Test deployment in Prod environment using Bicep template | Ava | 2022-12-19 | 2022-12-19 | 1 day | 9 | Bicep Template - Deploy | Achroo | Not Started | 9
Azure Functions Configurations | [5 empty] | Azure Function Configuration
Setup VS code environemnt | Ava | 2022-11-11 | 2022-11-12 | 1 day | 5 | Azure Function Configuration | Jamil | Complete | 0
Setup Azure environment linking Key Vault with managed identity | Ava | 2022-11-12 | 2022-11-12 | 1 day | 6 | Azure Function Configuration | Jamil | Complete | 0
Develop python script using http trigger function | Ava | 2022-11-12 | 2022-11-12 | 1 day | 4 | Azure Function Configuration | Jamil | Complete | 0
Develop python script reading stored secrets in Key Vault | Ava | 2022-11-13 | 2022-11-13 | 1 day | 8 | Azure Function Configuration | Jamil | Complete | 0
Develop python script private endpoint | Ava | 2022-11-14 | 2022-11-14 | 1 day | 10 | Azure Function Configuration | Jamil | Complete | 5 | Nov. 14 target to complete today
Encryption/Decryption | AVa |  |  |  | 0 | Azure Function Configuration | Jamil | Not Started |  | ADF to trigger the encryption/decryption
Start/Stop/Terminate VM | AVa |  | 2022-11-18 |  | 18 | Azure Function Configuration | Jamil | In-progress | 9 | Target to complete on or before Friday 18 Nov
Report status to JIRA | AVa |  | 2022-11-18 |  | 18 | Azure Function Configuration | Jamil | In-progress | 9 | Target to complete on or before Friday
Develop Python script for SQL DB |  |  | 2022-11-18 |  | 9 | Azure Function Configuration |  | Complete | 0
Testing Python script for SQL DB for private endpoints |  |  | 2022-11-18 |  | 9 | Azure Function Configuration |  | In-progress | 9
Develop PowerShell Code | [8 empty] | 0
1. Script to read data from keyvault (Encryption/Decryption key, stored as secret) | Ava | 2022-11-02 | 2022-11-03 | 2 days | 36 | PowerShell Script | JC Penny | Complete | 0
2. 1 Scrip to to write data to SQL | Ava | 2022-11-04 | 2022-11-07 | 2 days | 36 | PowerShell Script | JC Penny | Complete | 0
2. 1 Scrip to to read data to SQL | Ava | 2022-11-08 | 2022-11-09 | 2 days | 36 | PowerShell Script | JC Penny | Complete | 0
3. Script to stop vm, script to start vm (no public ip) | Ava | 2022-11-10 | 2022-11-11 | 2 days | 36 | PowerShell Script | JC Penny | Complete | 0
4. Copy a file (demo.zip/encrypted with key) from storage account blob location (private) to a disk | Ava | 2022-11-09 | 2022-11-09 | 1 day | 18 | PowerShell Script | JC Penny | Complete | 0
4.1 Unzip and extract to Disk2 | Ava | 2022-11-10 | 2022-11-10 | 1 day | 18 | PowerShell Script | JC Penny | Complete | 0
4.2 copy file from Disk2 to Storage location | Ava | 2022-11-11 | 2022-11-11 | 1 day | 18 | PowerShell Script | JC Penny | Complete | 0
4.3 read file from Disk2, zip and encrypt the file with the secret, write the secret in keyvault and copy it to Disk3 | Ava | 2022-11-14 | 2022-11-14 | 1 day | 18 | PowerShell Script | JC Penny | Complete | 0
4.4 copy zip file from Disk3 to SFTP location | Ava | 2022-11-15 | 2022-11-15 | 1 day | 18 | PowerShell Script | JC Penny | Complete | 0
5. Create Master Script to call different ps1 file | Ava | 2022-11-16 | 2022-11-18 | 3 days | 54 | PowerShell Script | Joseph | Complete | 0
6. Script to read-update Jira task | Ava | 2022-11-21 | 2022-11-22 | 2 days | 36 | PowerShell Script | JC Penny | Not Started | 36 | Azure Function (Jamil)
Test PowerShell code in Non-prod | Ava | 2022-11-23 | 2022-11-23 | 1 day | 18 | PowerShell Script - Test | JC Penny | Not Started | 54
Submit PoserShell code to CFS (John S.) for review | CFS | 2022-11-16 | 2022-11-21 | 0 day | 0 | PowerShell Script | JC Penny |  | 0
Update PowerShell code based on feedback and send for sign-off | Ava | 2022-11-24 | 2022-11-24 | 1 day | 18 | PowerShell Script | JC Penny | Not Started | 18
Approve/signoff PowerShell code | CFS | 2022-11-25 | 2022-11-25 | 0.5 days | 0 | PowerShell Script |  |  | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 0.5 | 9 | PowerShell Script | JC Penny | Not Started | 3
Deploy to Pre-prod environment | Ava | 2022-11-18 | 2022-11-18 | 0.5 | 9 | PowerShell Script - Deploy | JC Penny | Not Started | 3
Test deployment in pre-prod | Ava | 2022-11-18 | 2022-11-18 | 0.5 | 9 | PowerShell Script - Test | JC Penny | Not Started | 3
Deploy in Prod environment | Ava |  |  | 0.5 | 9 | PowerShell Script - Deploy | JC Penny | Not Started | 4
Test deployment in Prod environment | Ava | 2022-11-21 | 2022-11-21 | 1 | 18 | PowerShell Script | JC Penny | Not Started | 18
Azure DevOps – Pipeline | Ava | 2022-11-17 | 2022-11-24 | 6 | 48 | DeVops Pipeline | Achroo | Not Started | 45 | *Achroo to provide breakdown of tasks
Github action | Ava | 2022-11-21 | 2022-11-21 | 1 day | 8 | DeVops Pipeline | Achroo | Complete | 0
yml file creation / pipeline for one time resources | Ava | 2022-11-22 | 2022-11-22 | 1 day | 8 | DeVops Pipeline | Achroo | In-progress | 8
pipeline for adhoc resources | Ava | 2022-11-23 | 2022-11-24 | 2 days | 16 | DeVops Pipeline | Achroo | Not Started
Testing | Ava | 2022-11-25 | 2022-11-28 | 2 days | 16 | DeVops Pipeline | Achroo | Not Started
GitHub Enterprise Cloud | CFS |  |  |  |  | Github
Provision SFTP |  | 2022-10-24 08:00 | 2022-12-01 17:00 | 29 days |  | SFTP
Finalize Design | Ava | 2022-10-24 08:00 | 2022-10-27 17:00 | 4 days | 36 | SFTP | Deep | Complete | 0
Create template | Ava | 2022-10-28 08:00 | 2022-11-03 17:00 | 5 days | 45 | SFTP | Infra (Jojo) | Complete | 0
Test deployment of SFTP in Non-prod using template |  | 2022-11-04 08:00 | 2022-11-14 17:00 | 7 days |  |  |  |  | 0
Submit template to CFS (John S.) for review | CFS | 2022-11-04 08:00 | 2022-11-07 17:00 | 2 days | 0 | SFTP | Infra (Jojo) | Complete | 0
Update template based on feedback and send for sign-off | Ava | 2022-11-08 08:00 | 2022-11-15 17:00 | 5 days | 40 | SFTP | Infra (Jojo) | Complete | 0
Approve/signoff Bicep template | CFS | 2022-11-09 08:00 | 2022-11-09 17:00 | 1 day | 0 | SFTP | Infra (Jojo) | Complete | 0
Commit code to github | Ava | 2022-11-25 | 2022-11-25 | 1 day | 4 | SFTP | Infra (Jojo) | Not Started | 4
Deploy to Pre-prod environment using Bicep template | Ava | 2022-11-28 | 2022-11-28 | 1 day | 9 | SFTP | Infra (Jojo) | Not Started | 9
Test deployment in pre-prod using Bicep template | Ava | 2022-11-29 | 2022-11-29 | 1 day | 9 | SFTP | Infra (Jojo) | Not Started | 0
Deploy in Prod environment using Bicep template | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | SFTP - Deploy | Infra (Jojo) | Not Started | 9
Test deployment in Prod environment using Bicep template | Ava | 2022-12-19 | 2022-12-19 | 1 day | 9 | SFTP - Test | Infra (Jojo) | Not Started | 9
Build and unit-test ADF Automated Pipeline |  |  |  |  | 0 | ADF Pipeline |  |  | 0
Create Azure Data Factory Pipelines | Ava | 2022-11-07 | 2022-11-30 | [5 empty] | ETC | 11/14/2022 - Review Design Doc with Rye. Sent the initial doc to Amandeep - Jen 11/11/2022 - finished creating the initial Design Doc for ADF. Will set a meeting to Achroo to review. (Jen) 1/10/2022 - Infra Team building the azure resources for Data Team (Jen) 11/9/2022 - Jen - Had a meeting with Achroo to verify the process. Will now build the ADF on the resource group prepared by Achroo which is self hosted. Design Doc now in progress
SQL tables | Ava | 2022-11-17 | 2022-11-17 |  | 9 | ADF Pipeline | Jennifer | Complete | 0 | Ely: As per discussion on 17 Nov, Jennifer confirmed this is complete?
Validate parameters from Jira (or parameter source) | Ava | 2022-11-17 | 2022-11-18 |  | 18 | ADF Pipeline | Jeramel | In-progress | 9
Internal Usage - Flow 1 | [7 empty] | In-progress
Unzipping of files (Get Metadata, For Each and Copy Activity) | Ava | 2022-11-09 | 2022-11-10 |  | 18 | ADF Pipeline | Jennifer | Complete | 0 | unzipping of files will be in PoweShell script
Decryption of file (integration of Azure function) | Ava | 2022-11-17 | 2022-11-18 |  | 18 | ADF Pipeline | Jennifer | In-progress | 9 | Integration (calling) of Azure Function/Powershell script
Copy Data Activity from SFTP (to LZone) to CFS Storage Account | Ava | 2022-11-21 | 2022-11-22 |  | 18 | ADF Pipeline | Jeramel | In-progress | 9 | Need to try with CBA SFTP server.
Write Logs to Azure SQL Server table | Ava | 2022-11-21 | 2022-11-22 |  | 18 | ADF Pipeline | Jennifer | Not Started | 18
Enternal Usage - Flow 2 | [7 empty] | In-progress
Unzipping of files (Get Metadata, For Each and Copy Activity) | Ava | 2022-11-11 | 2022-11-12 |  | 18 | ADF Pipeline | Jeramel | Complete | 0
Encryption/Decryption of file (integration of Azure function) | Ava | 2022-11-22 | 2022-11-23 |  | 18 | ADF Pipeline | Jeramel | In-progress | 18 | Integration (calling) of Azure Function/Powershell script
Copy Data Activity from SFTP (to LZone) to CFS SFTP (as Blob) | Ava | 2022-11-24 | 2022-11-25 |  | 18 | ADF Pipeline | Jeramel | In-progress | 18
Create ADF Link Services | Ava |  |  |  |  | ADF Pipeline |  | In-progress
Create Linked Service for CBA SFTP |  | 2022-11-25 | 2022-11-25 |  | 9 | ADF Pipeline |  | Not Started | 9
Create Linked Service for Landing Zone (Blob Storage) |  | 2022-11-28 | 2022-11-28 |  | 9 | ADF Pipeline |  | Not Started | 9
Create Linked Service for JIRA |  | 2022-11-29 | 2022-11-29 |  | 9 | ADF Pipeline |  | Not Started | 9
Create Linked Service for CFS SFTP Target | Ava | 2022-11-15 | 2022-11-15 |  | 9 | ADF Pipeline | Jennifer | Complete | 0
Create Linked Service for Blob Storage Target | Ava | 2022-11-16 | 2022-11-16 |  | 9 | ADF Pipeline | Jennifer | Complete | 0
Create Azure function that calls key from KeyVault | Ava | 2022-11-17 | 2022-11-18 |  | 0 | ADF Pipeline | Jennifer | Complete | 0 | will be done by Azure Function resource
Create Azure function that encrypt/decrpyt file | Ava | 2022-11-17 | 2022-11-22 |  | 0 | ADF Pipeline | Jeramel | Not Started | 0 | will be done by Azure Function resource
Create Linked Service for Azure Key Vault | Ava | 2022-11-09 | 2022-11-09 |  | 9 | ADF Pipeline | Jeramel | Complete | 0
Create Linked Service for SQL server | Ava | 2022-11-10 | 2022-11-10 |  | 9 | ADF Pipeline | Jeramel | Complete | 0
Create Linked Service for Azure function | Ava | 2022-11-11 | 2022-11-14 |  | 18 | ADF Pipeline | Jennifer | Complete | 0
Create ADF Data Sets | Ava | 2022-11-07 | 2022-11-08 |  |  | ADF Pipeline |  | In-progress
Create datasets for destination | Ava | 2022-11-14 | 2022-11-14 |  | 9 | ADF Pipeline | Jennifer | Complete | 0
Create datasets for source | Ava | 2022-11-15 | 2022-11-15 |  | 9 | ADF Pipeline | Jennifer | Complete | 0
Create datasets for get metadata | Ava | 2022-11-23 | 2022-11-24 |  | 18 | ADF Pipeline | Jennifer | In-progress | 18
Test Pipeline and fix-it | Ava | 2022-11-25 | 2022-11-30 | 4 days | 72 | ADF Pipeline - Test | Jennifer Jeramel | Not Started | 72
Deploy to Prod environment | Ava | 2022-12-16 | 2022-12-16 | 1 day | 9 | ADF Pipeline - Deploy | Jennifer | Not Started | 9
Test deployment in Prod | Ava | 2022-12-19 | 2022-12-19 | 1 day | 9 | ADF Pipeline - Test | Jennifer | Not Started | 9
Build script to generate Encryption keys | Ava
Build script to generage AES128 encryption | Ava | 2022-10-10 | 2022-10-10 |  |  | Security | Jay | In-progress | ? | Ely: Please provide estimates for remaining hours needed
Generate PGP Keys through Linux | Ava | 2022-10-10 | 2022-10-21 | 11 days | 110 | Security | Jay/Clarissa | Complete | 0
Test script | Ava | 2022-10-10 | 2022-10-21 | 11 days | 110 | Security | Jay/Clarissa | Complete | 0
Create document | Ava | 2022-10-17 | 2022-10-21 | 5 days | 50 | Security | Jay/Clarissa | Complete | 0
Integration Testing and Fix-it | Ava | 2022-11-14 | 2022-11-29 | 12 days | 0 |  |  |  | 0
SFTP | Ava | 2022-11-14 | 2022-11-29 | 12 days | 96 |  |  |  | 96 | 9 Nov: Deep to email Priyank
Infra Components | Ava | 2022-11-14 | 2022-11-29 | 12 days | 204 |  |  |  | 204
PowerShell Scripts | Ava | 2022-11-14 | 2022-11-29 | 12 days | 216 |  |  |  | 216
ADF Pipelien | Ava | 2022-11-14 | 2022-11-29 | 12 days | 216 |  |  |  | 216
Script for PGP keys | Ava | 2022-11-14 | 2022-11-29 | 12 days | 108 |  |  |  | 108
|  |  | Total Build Hours |  | 2716
|  |  | Overall Total Hours |  | 3556